## Sheet1
S.NO | NAME | 2025-10-28 | Percentage | 2025-10-31 | Percentage | 2025-11-06 | Percentage | 2025-11-07 | Percentage | TOTAL PERCENTAGE
1 | VELUMRGAN SRIRAM | Documentation of theproject needs and technical document | 5% | Documentation of theproject needs and technical document | 20% | Worked on github and process | 40% | Working on the share Sharepoint online site | 70% | 85%
2 | CHAKKA SRIRAM | Preparation of the gantt chart | 5% | Preparation of the gantt chart | 25% | Sharepoint online | 35% | Working on thw power bi | 75% | 80%
3 | NANDINI VADLA | Preparation of the share points and modifying the correctiom | 5% | Preparation of the share points and modifying the correctiom | 22% | Mamaging the data base and tracking | 40% | Working on the excel sheet to track the project | 70% | 85%
4 | MARUTURI NIKHIL | Installed and exploring the power bi to get the maximum usage | 5% | Installed and exploring the power bi to get the maximum usage | 20% | Microsoft power bi | 30% | Working on the power bi | 60% | 75%
5 | YERRIBOINA AVINASH | Preparaton of technical documents | 5% | Preparaton of technical documents | 20% | Worked on the technical project | 30% | Working on the technical project | 50% | 70%
5